Document Number

xxxx.999.00.001

Topic

The existing testing tools „Panel“ and "Gameboy" have to be merged into one configurable version. Currently LGIC is interested in a special PANEL version.

| Project Info |  |
| --- | --- |
| Manager: | FR |
| Resources: | FR, RK |
| Start: | 05.04.2000 |
| End: | September |
| Manpower: |  |
| PS7 Status: | -- |

| History |  |  |  |
| --- | --- | --- | --- |
| Date | Vers. | Author | Description |
| 16.03.00 | 001 | FR | Initial |
| 12.05.00 | 002 | RK | effort calculation |
| 25.05.00 | 003 | RK | Recalculation, full translation |

| Milestones/Deliverables |  |  |
| --- | --- | --- |
| Date | PS7 Name | Description |

# Brief Problem Description:

LGIC would like to have their own costumer spezific PANEL solution. They have provided the keyboard layout and the LCD display size and expect a panel with that design and corresponding   functionality: Key-Code connection and graphical display response.

To avoid another proprietary „isolated solution“ only one new panel will be implemented with the functionality of the former „Panel“ and the „Gameboy“ insight. This merged and extended „xPanel“ will have a configurable layout as well. The costumers himself should be able to do configuration and creation of new layouts.

At the same time the two existing mechanisms for transmission of graphical display data (MMITAP, Gameboy) will be merged into one solution.

# Estimated Effort

The following table contains the currently estimated minimal efforts:

| Task | Who | Hours | Hours finished |
| --- | --- | --- | --- |
| Tcl/Tk-Einarbeitung | RK | 12 | 10 |
| Frame-Einarbeitung | RK | 36 | 29 |
| Konzept u. Spezifikation xPanel | RK | 36 | 15 |
| Tcl/Tk-Frontend implementation | RK | 24 | 8 |
| C-Backend implementation | RK | 98 | 10 |
| Know-How-Transfer | ES/ RK | 2 | 2 |
| Test | RK | 24 |  |
| Userguide erstellen (mit Konfigurationsbeschreibung) | RK | 24 |  |
| Summe |  | 256 | 74 |

Ronny Kiessling (RK) currently works 12 hours a week.